## Tabelle1
UC Name | Documentation | Development | Testing | Design | Deployment | Research | Total w/o warmup | Total | Estimate | FP | Explaniation
Register | 0:00 | 20:30 | 0:00 | 0:00 | 0:00 | 0:00 | 20:30 | 20:30 | 15:24 | 13
Login | 0:00 | 6:00 | 0:00 | 0:00 | 0:15 | 0:00 | 6:15 | 6:15 | 29:17 | 24.7
Register/Login Google | 1:10 | 21:10 | 0:00 | 0:00 | 0:00 | 0:00 | 22:20 | 22:20 | 30:49 | 26
Edit Profile | 0:50 | 1:45 | 1:30 | 0:00 | 0:00 | 0:00 | 4:05 | 4:05 | 0:00
Change Password | 0:50 | 1:45 | 1:30 | 0:00 | 0:00 | 0:00 | 4:05 | 4:05 | 0:00
Delete User | 0:00 | 4:50 | 0:00 | 0:00 | 0:00 | 0:00 | 4:50 | 4:50 | 0:00
Search User | 0:00 | 6:00 | 2:00 | 0:00 | 0:00 | 0:00 | 8:00 | 8:00 | 0:00
Add Friend | 0:00 | 2:35 | 1:00 | 0:00 | 0:00 | 0:00 | 3:35 | 3:35 | 0:00
List Received Friend Requests | 0:55 | 0:55 | 0:00 | 0:00 | 0:00 | 0:00 | 1:50 | 1:50 | 0:00
List Sent Friend Requests | 0:55 | 0:55 | 0:00 | 0:00 | 0:00 | 0:00 | 1:50 | 1:50 | 0:00
Accept Friend Request | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
Delete Friend | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
Create New Request | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
Create New Offer | 0:00 | 10:23 | 1:45 | 0:00 | 0:00 | 0:00 | 12:08 | 12:08 | 0:00
Search Offer and Requests | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
List Requests | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
List Offers | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
Edit Status | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
Login | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 1 | 3 |  | 13
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 3 | 6
Number of Files (ILF) | 1 | 1 | 0 | 0 | 1 | 3 | 7 |  |  |  |  | Time spent (w/o outliers) | Function Points (w/o outliers) | Velocity
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 75.5 | 63.7 | 0.84371
Register | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 5 | 0 | 1 | 0 | 2 | 6 | 20 |  | 24.7
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 2 | 6 | 14
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Register/Login_Google | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 3 | 0 | 1 | 0 | 2 | 6 | 12 |  | 26
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 2 | 6 | 14
Number of External Interfaces (EIF) | 2 | 1 | 0 | 0 | 2 | 6 | 10
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 1 | 3 | The amount depends on the survey in the database. That makes presenting the survey more comlex | 18.9
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 0 | 3
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | Presenter, Bar Model, Question Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 13.65
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 2 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 1 | 3
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 2 | 14 | Presenter, Bar
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 18.2
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 5 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 2 | 0 | 3
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | View, Presenter, Database, Model,
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 0 | 1 | 0 | 1 | 25 | 4 | 25 single, clickable stars | 17.5
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 3 | 1 | 0 | 0 | 1 | 11 | 21 | Presenter, Rating Class, Bar Class. Influences many fields in the database
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 1 | 3 |  | 11.05
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 10 | 1 | 0 | 0 | 1 | 10 | 30 |  | 28.6
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, User Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) |  | 1 | 0 | 0 | 0 | 0 | 0 |  | 20.15
Number of User Outputs (EO) |  | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 0 | 3 |  | 23.8827
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | Presenter, Bar Model, Map Class
Number of External Interfaces (EIF) | 1 | 0 | 1 | 0 | 5 | 30 | 7 | Google Maps
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 1 | 3 | A Tag will be saved | 11.05
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 13.0969
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Spalte1 | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 4 | 1 | 0 | 0 | 0 | 4 | 12 | A complete bar needs to be saved | 16.9
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 20.0306
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presnter, Bar Class
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Name | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0