## Tabelle1
UC Name | Documentation | Development | Testing | Design | Deployment | Research | Total w/o warmup | Total | Estimate | FP | Explaniation
Register | 0:00 | 20:30 | 0:00 | 0:00 | 0:00 | 0:00 | 20:30 | 20:30 | 11:56 | 35.1 | Outlier because first use case
Login | 2:00 | 6:00 | 0:00 | 0:00 | 0:15 | 0:00 | 8:15 | 8:15 | 5:58 | 17.55
Register/Login Google | 1:10 | 21:10 | 0:00 | 0:00 | 0:00 | 0:00 | 22:20 | 22:20 | 11:29 | 33.8 | Outlier because lot of trying
Edit Profile | 0:50 | 1:45 | 1:30 | 0:00 | 0:00 | 0:00 | 4:05 | 4:05 | 6:40 | 19.6
Change Password | 0:50 | 1:45 | 1:30 | 0:00 | 0:00 | 0:00 | 4:05 | 4:05 | 4:12 | 12.35
Delete User | 0:00 | 4:50 | 0:00 | 0:00 | 0:00 | 0:00 | 4:50 | 4:50 | 4:12 | 12.35
Search User | 0:50 | 6:00 | 2:00 | 0:00 | 0:00 | 0:00 | 8:50 | 8:50 | 9:30 | 27.95
Add Friend | 0:50 | 2:35 | 1:00 | 0:00 | 0:00 | 0:00 | 4:25 | 4:25 | 5:05 | 14.95
List Received Friend Requests | 0:55 | 0:55 | 0:00 | 0:00 | 0:00 | 0:00 | 1:50 | 1:50 | 5:18 | 15.6
List Sent Friend Requests | 0:55 | 0:55 | 0:00 | 0:00 | 0:00 | 0:00 | 1:50 | 1:50 | 4:25 | 13
Accept Friend Request | 0:20 | 0:50 | 0:35 | 0:00 | 0:00 | 0:00 | 1:45 | 1:45 | 7:57 | 23.4
Delete Friend | 0:50 | 1:40 | 0:30 | 0:00 | 0:00 | 0:00 | 3:00 | 3:00 | 5:45 | 16.9
Create New Request | 1:40 | 0:45 | 1:00 | 0:00 | 0:00 | 0:00 | 3:25 | 3:25 | 9:56 | 29.25
Create New Offer | 1:00 | 10:23 | 1:45 | 0:00 | 0:00 | 0:00 | 13:08 | 13:08 | 9:56 | 29.25
Search Offer and Requests | 0:40 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:40 | 0:40 | 7:31 | 22.1
List Requests | 0:40 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:40 | 0:40 | 4:38 | 13.65
List Offers | 0:50 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:50 | 0:50 | 4:38 | 13.65
Edit Status | 0:35 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:35 | 0:35 | 4:38 | 13.65
Login | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 1 | 4 | 6 |  | 17.55
Number of User Outputs (EO) | 2 | 1 | 0 | 0 | 1 | 16 | 8
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 1 | 1 | 0 | 0 | 1 | 16 | 7 |  |  |  |  | Time spent (w/o outliers) | Function Points (w/o outliers) | Velocity
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 102.3 | 301.05 | 2.9428
Register | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 5 | 0 | 0 | 1 | 2 | 21 | 30 |  | 35.1
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 16 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 1 | 0 | 0 | 2 | 16 | 14
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Register/Login_Google | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 3 | 0 | 0 | 1 | 2 | 21 | 18 |  | 33.8
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 16 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 1 | 0 | 0 | 2 | 17 | 14
Number of External Interfaces (EIF) | 2 | 1 | 0 | 0 | 4 | 14 | 10
Edit Profile | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 3 | 1 | 0 | 0 | 2 | 3 | 9 | The amount depends on the survey in the database. That makes presenting the survey more comlex | 19.6
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 16 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 1 | 0 | 0 | 1 | 16 | 7
Number of External Interfaces (EIF) | 1 | 1 | 0 | 0 | 0 | 0 | 5
Change Password | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 3 | 1 | 0 | 0 | 1 | 1 | 9 |  | 12.35
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 16 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 0 | 1 | 0 | 0 | 1 | 18 | 0
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Delete User | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 0 | 0 | 1 | 2 | 23 | 12 |  | 27.95
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 3 | 1 | 0 | 0 | 1 | 16 | 21
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Search User | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 0 | 0 | 6 |  | 14
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 8 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 1 | 0 | 0 | 2 | 8 | 7
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Add Friend | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 2 | 3 |  | 14.95
Number of User Outputs (EO) | 1 | 0 | 0 | 1 | 2 | 32 | 7
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 0 | 1 | 0 | 3 | 32 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
List Received Friend Requests | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 1 | 1 | 6 |  | 15.6
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 5 | 4
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 1 | 1 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 2 | 5 | 14
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
List Sent Friend Requests | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 1 | 3 |  | 13
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 5 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6 |  | 4.4175
Number of Files (ILF) | 1 | 1 | 0 | 0 | 2 | 5 | 7
Number of External Interfaces (EIF) | 0 | 0 | 1 | 0 | 5 | 30 | 0
Accept Friend Request | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 2 | 3 |  | 23.4
Number of User Outputs (EO) | 1 | 0 | 0 | 1 | 2 | 32 | 7
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6 |  | 7.9516
Number of Files (ILF) | 2 | 0 | 1 | 0 | 2 | 32 | 20
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Delete Friend | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 2 | 3 |  | 16.9
Number of User Outputs (EO) | 1 | 0 | 0 | 1 | 2 | 32 | 7
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6 |  | 5.7428
Number of Files (ILF) | 1 | 0 | 1 | 0 | 2 | 32 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Create New Request | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 5 | 1 | 0 | 0 | 1 | 10 | 15 |  | 29.25
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 0 | 1 | 0 | 3 | 29 | 20
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Create New Offer | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 5 | 1 | 0 | 0 | 1 | 10 | 15 |  | 29.25
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 0 | 1 | 0 | 3 | 29 | 20
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Search Offer and Requests | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 0 | 0 | 6 |  | 22.1
Number of User Outputs (EO) | 1 | 0 | 1 | 0 | 4 | 10 | 5
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 2 | 0 | 1 | 0 | 3 | 29 | 20
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
List Requests | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 |  | 13.65
Number of User Outputs (EO) | 1 | 0 | 1 | 0 | 4 | 10 | 5
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 0 | 1 | 0 | 3 | 29 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
List Offers | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 |  | 13.65
Number of User Outputs (EO) | 1 | 0 | 1 | 0 | 4 | 10 | 5
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 0 | 1 | 0 | 3 | 29 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Edit Status | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 |  | 13.65
Number of User Outputs (EO) | 1 | 0 | 1 | 0 | 3 | 10 | 5
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 0 | 1 | 0 | 3 | 29 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0