## Tabelle1
UC Name | Documentation | Development | Testing | Design | Deployment | Research | Total w/o warmup | Total | Estimate | FP | Explaniation
Register | 0:00 | 20:30 | 0:00 | 0:00 | 0:00 | 0:00 | 20:30 | 20:30 | 11:59 | 54 | Outlier because first use case
Login | 2:00 | 6:00 | 0:00 | 0:00 | 0:15 | 0:00 | 8:15 | 8:15 | 5:59 | 27
Register/Login Google | 1:10 | 21:10 | 0:00 | 0:00 | 0:00 | 0:00 | 22:20 | 22:20 | 11:32 | 52 | Outlier because lot of trying
Edit Profile | 0:50 | 1:45 | 1:30 | 0:00 | 0:00 | 0:00 | 4:05 | 4:05 | 6:13 | 28
Change Password | 0:50 | 1:45 | 1:30 | 0:00 | 0:00 | 0:00 | 4:05 | 4:05 | 4:13 | 19
Delete User | 0:00 | 4:50 | 0:00 | 0:00 | 0:00 | 0:00 | 4:50 | 4:50 | 4:13 | 19
Search User | 0:50 | 6:00 | 2:00 | 0:00 | 0:00 | 0:00 | 8:50 | 8:50 | 9:33 | 43
Add Friend | 0:50 | 2:35 | 1:00 | 0:00 | 0:00 | 0:00 | 4:25 | 4:25 | 5:06 | 23
List Received Friend Requests | 0:55 | 0:55 | 0:00 | 0:00 | 0:00 | 0:00 | 1:50 | 1:50 | 5:20 | 24
List Sent Friend Requests | 0:55 | 0:55 | 0:00 | 0:00 | 0:00 | 0:00 | 1:50 | 1:50 | 4:26 | 20
Accept Friend Request | 0:20 | 0:50 | 0:35 | 0:00 | 0:00 | 0:00 | 1:45 | 1:45 | 7:59 | 36
Delete Friend | 0:50 | 1:40 | 0:30 | 0:00 | 0:00 | 0:00 | 3:00 | 3:00 | 5:46 | 26
Create New Request | 1:40 | 0:45 | 1:00 | 0:00 | 0:00 | 0:00 | 3:25 | 3:25 | 9:59 | 45
Create New Offer | 1:00 | 10:23 | 1:45 | 0:00 | 0:00 | 0:00 | 13:08 | 13:08 | 9:59 | 45
Search Offer and Requests | 0:40 | 1:50 | 0:00 | 0:00 | 0:00 | 0:00 | 2:30 | 2:30 | 7:33 | 34
List Requests | 0:40 | 1:30 | 0:00 | 0:00 | 0:00 | 0:00 | 2:10 | 2:10 | 4:40 | 21
List Offers | 0:50 | 1:59 | 0:00 | 0:00 | 0:00 | 0:00 | 2:49 | 2:49 | 4:40 | 21
Edit Status | 0:35 | 1:40 | 0:50 | 0:00 | 0:00 | 0:00 | 3:05 | 3:05 | 4:40 | 21
Login | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 1 | 4 | 6 |  | 27
Number of User Outputs (EO) | 2 | 1 | 0 | 0 | 1 | 16 | 8
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 1 | 1 | 0 | 0 | 1 | 16 | 7
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Register | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 5 | 0 | 0 | 1 | 2 | 21 | 30 |  | 54
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 16 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 1 | 0 | 0 | 2 | 16 | 14
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Register/Login_Google | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 3 | 0 | 0 | 1 | 2 | 21 | 18 |  | 52
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 16 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 1 | 0 | 0 | 2 | 17 | 14
Number of External Interfaces (EIF) | 2 | 1 | 0 | 0 | 4 | 14 | 10
Edit Profile | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 3 | 1 | 0 | 0 | 2 | 3 | 9 |  | 28
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 16 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 1 | 0 | 0 | 1 | 16 | 7
Number of External Interfaces (EIF) | 1 | 1 | 0 | 0 | 0 | 0 | 5 |  |  |  |  | Time spent (w/o outliers) | Function Points (w/o outliers) | Velocity
[12 empty] | 102.3 | 461 | 4.5064
Change Password | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 3 | 1 | 0 | 0 | 1 | 1 | 9 |  | 19
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 16 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 0 | 1 | 0 | 0 | 1 | 18 | 0
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Delete User | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 0 | 0 | 1 | 2 | 23 | 12 |  | 43
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 3 | 1 | 0 | 0 | 1 | 16 | 21
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Search User | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 0 | 0 | 6 |  | 20
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 8 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 1 | 0 | 0 | 2 | 8 | 7
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Add Friend | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 2 | 3 |  | 23
Number of User Outputs (EO) | 1 | 0 | 0 | 1 | 2 | 32 | 7
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 0 | 1 | 0 | 3 | 32 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
List Received Friend Requests | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 1 | 1 | 6 |  | 24
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 5 | 4
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 1 | 1 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 2 | 5 | 14
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
List Sent Friend Requests | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 1 | 3 |  | 20
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 5 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 1 | 1 | 0 | 0 | 2 | 5 | 7
Number of External Interfaces (EIF) | 0 | 0 | 1 | 0 | 5 | 30 | 0
Accept Friend Request | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 2 | 3 |  | 36
Number of User Outputs (EO) | 1 | 0 | 0 | 1 | 2 | 32 | 7
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 0 | 1 | 0 | 2 | 32 | 20
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Delete Friend | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 2 | 3 |  | 26
Number of User Outputs (EO) | 1 | 0 | 0 | 1 | 2 | 32 | 7
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 1 | 0 | 1 | 0 | 2 | 32 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Create New Request | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 5 | 1 | 0 | 0 | 1 | 10 | 15 |  | 45
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 0 | 1 | 0 | 3 | 29 | 20
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Create New Offer | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 5 | 1 | 0 | 0 | 1 | 10 | 15 |  | 45
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 1 | 4
Number of User Inquiries (EQ) | 2 | 1 | 0 | 0 | 1 | 1 | 6
Number of Files (ILF) | 2 | 0 | 1 | 0 | 3 | 29 | 20
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Search Offer and Requests | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 0 | 0 | 6 |  | 34
Number of User Outputs (EO) | 1 | 0 | 1 | 0 | 4 | 10 | 5
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 2 | 0 | 1 | 0 | 3 | 29 | 20
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
List Requests | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 |  | 21
Number of User Outputs (EO) | 1 | 0 | 1 | 0 | 4 | 10 | 5
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 0 | 1 | 0 | 3 | 29 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
List Offers | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 |  | 21
Number of User Outputs (EO) | 1 | 0 | 1 | 0 | 4 | 10 | 5
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 0 | 1 | 0 | 3 | 29 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Edit Status | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 |  | 21
Number of User Outputs (EO) | 1 | 0 | 1 | 0 | 3 | 10 | 5
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 1 | 1 | 3
Number of Files (ILF) | 1 | 0 | 1 | 0 | 3 | 29 | 10
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0