## Tabelle1
Identified | prob of occurrence | damage | mitigation strategy | person in charge | Risk factor
Erroneous time planning | 20% | 7 | Detailed time plans for use cases | Waldemar Merk | 1.4
System outages | 10% | 10 | Building a redundant infrastructure | Gabriel Zachmann | 1
Personnel deficits | 5% | 5 | Defining backup roles | Patrick Treyer | 0.25
Requirements are incomplete | 7% | 3 | Writing detailed use case descriptions | Gabriel Zachmann | 0.21
Under communication | 5% | 2 | Organizing weekly meetings | Patrick Treyer | 0.1
Low team motivation | 2% | 4 | Declare strict deadlines | Waldemar Merk | 0.08
Technical impossibilities | 3% | 2 | Searching for alternatives | Waldemar Merk | 0.06
Design is not fit for purpose | 2% | 3 | Hire teams to review the designs | Patrick Treyer | 0.06
Resources are inexperienced | 5% | 1 | Reserving time for training | Gabriel Zachmann | 0.05